| School Improvement Plan –Literacy Geashill NS Published: June 2014 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Summary of main strengths as indentified in last SSE (June2013) | - Attainment levels in literacy are above national norms. - Pupils, parents and teachers see writing as an important part of curriculum. - The children’s written work is valued and displayed throughout the school. - The teaching of writing is very good. - Children make good use of ITC in the presentation of writing. - The standard of writing in many cases is very good. |  |  |  |
| Summary of main areas requiring improvements as identified in last SSE | - Increase the opportunities given to children to write collaboratively in pairs and in groups - Continue to source samples of each writing genre suitable for each class level - The teaching of writing process needs to be further developed throughout the school - Children need to write in a wider variety of genres. - Assessment of writing needs to be further developed. - Provide professional development for teachers to aid the teaching of writing process - Teaching of grammar, spelling, syntax and punctuation needs attention |  |  |  |
| Improvement Targets Writing | Required Actions | Persons Responsible | Timeframe for actions | Review Dates |
|  | YEAR ONE |  |  |  |
| - By the end of year 3 children in all class levels will be at the appropriate level on a staff designed writing rubric - By the end of year 2 all children will experience writing in the different genres | - Review assessment practices for writing in the school | All staff | Year 1 | On going |
|  | - All staff will share good practice for writing and writing assessment | All staff | Year 1 | On Going |
|  | - Writing periods will be timetabled in all classes | All staff | Year 1 | On Going |
|  | - PM writing scheme will be used throughout the school | All Staff | Year 1 | On Going |
|  | - Narrative /Persuasive+Information Report genres will be taught | Class Teachers | Year 1 |  |
|  | YEAR TWO |  |  |  |
|  | - Design a writing rubric for use 1st, 6th, classes Drumcondra writing indicators to be used for junior and senior Infants. | Class Teachers | Term 2,3 | Term 3 |
|  | - Pilot use of identified assessment approaches writing portfolio, writing rubric | All Staff |  |  |
|  | - Review use of assessment tools. | All Staff | Term 3 |  |
|  | - Genres of Recount /Procedural/Explanation will be taught. | Class Teachers | Term 1,2,3 |  |
|  | Teachers will use staff designed writing rubric when assessing samples of pupil’s writing. | All Staff | Term 2,3 | Term 3 |
|  | Progress will be monitored during the year. | All Staff | Term 1,2,3 |  |
|  | Children will complete a writing checklist after completing written tasks. | All Staff | Term 2 | Term 3 |
|  | YEAR THREE |  |  |  |
|  | - Share the assessment approaches for writing with parents. | Class Teachers | Term 1 |  |
|  | - Analyse assessment records and approaches for writing. | All Staff | Term 2 |  |
|  | - Consolidate work on writing genres from year 1&2 | Class Teachers | Term 1,2,3 |  |
| Success Criteria/Measurable Outcomes Teachers are using the staff designed writing rubric when assessing samples of pupils’ writing e.g. writing copies, portfolios. Targets will be reviewed in relation to baseline data in term 3 each year. |  |  |  |  |
| Monitor and Review Progress and challenges will be reviewed during Croke Park hours. Agree and allocate time for monitoring actions. |  |  |  |  |